## Slide 1: Hartford’s Promise
Planning the Plan
May 28, 2010
grantify

## Slide 2: Key Tasks
Identifying Partners
Determining Indicators
Crafting a Theory of Change/Theory of Action

## Slide 3: Our Timeline
Task | Due Date | Responsible Person
Draft of Logic Model and theories of Action/Change | June 4, 2010 | Keith Whitescarver
Partnering Organizations Secured | June 15, 2010 | Jackie Cossentino
Data Analysis and Literature Review Compete | June 15, 2010 | Reanna Blackford
First Draft of Narrative Circulated | June 20, 2010 | Keith Whitescarver
Budget and Match Details Complete | June 20, 2010 | Keith Whitescarver & Jackie Cossentino
Second Draft of Narrative Circulated | June 23, 2010 | Keith Whitescarver
Proposal submitted | June 24, 2010 | Keith Whitescaver

## Slide 4: Coordinated Investment
Community Impact
Health
Schools
Housing
Partners
Partners
Partners

## Slide 5: Academic Goals & Indicators
Children ready for Kindergarten
Students proficient in core subjects
Successful Middle School to High School Transition
High School Graduation
College Career Success
% of young children who demonstrate age-appropriate functioning and participate in early learning programs
#/% of students at or above grade levels according to 3rd & 8th grade tests and high school assessments
Attendance rate in 6th, 7th, 8th grades
Graduate rate in neighborhood high school*
#/% of students with post-secondary degrees or credentials w/o remediation

## Slide 6: Social & Community Supports Goals and Indicators
Students are Healthy
Students Feel Safe
Students Live in Stable Communities
Family/Community Support Learning
21st Century Learning Tools
#/% of children who participate in 60 minutes of physical activity daily and eat five or more servings of fruits and vegetables daily
#/% of students who feel safe at school and traveling to and from school as measured by a climate survey
Student Mobility Rate
#/% of students with a caring adult at home, school, and community; or #/% of families that attend parent-teacher conferences
#/% of students with school and home access to broadband and connected computing device

## Slide 7: Coordinating Theories
Theory of Change
  What changes are we seeking?
  What causes those changes?
Theory of Action
  What are we going to do?
  Why do we think those action will bring about the outcome we’re after?

## Slide 8: Logic Model Template
Need
To revitalize a Hartford Neighborhood
To create a pathway of opportunity for the neighborhood’s children
Inputs
School Supports
Community Supports
Outputs
A more stable, safer, engaged neighborhood
More students who complete the pathways successfully
Outcome
Increased and better coordinated services
(as shown through data linked to indicators)

## Slide 9: During the planning year, grantees will:
Conduct a comprehensive needs assessment
Conduct a segmentation analysis
Develop a plan for a continuum of services
Work with other public and private agencies to ensure sustainability
Build on work by other place based initiatives (HUD – HOPE VI, Choice), (HHS – Health Centers), (Justice – Byrne Criminal Justice Innovation and Weed and Seed)
Community support and engagement
Develop a strategy to hold partners accountable for meeting performance goals and milestones
Plan, build, adapt or expand a comprehensive, longitudinal data management system
Work with national evaluator
Participate in a community of practice

## Slide 10: How to spend the 500k
Provide funding for the solution partners to align their data collection with the ETO data management system.
Funds to pilot new programs that are deemed necessary but are currently lacking. Partners, working with UConn experts, should/could develop these.
Financial support for elements of the school reform at SAND that are not yet in place.
Provide financial support for the following:
  Communications Team
  Fundraising/Development Team: this team is responsible for current funding assessment, securing match funding, and “tracking available sources and funding levels from federal, state, and local funds that could be used to support this project.”
  Data Team - Full time data person to manage and oversee getting everyone on board. Other supplemental support.